Sr. No………. (For office use only)

# APPLICATION FOR SELECTION OF ARCHITECT / ARCHITECTURAL FIRM

Name of the Applicant: 	M/s………………………………………………………..

Name of the work: 		Architectural Consultancy Work for the Construction of Administrative Office & Staff Residential Apartments at Sector 80, S.A.S. Nagar (Mohali), Punjab

Last date of submission:	17/07/2024 up to 3:00 pm

## Central Bank of India

ZONAL OFFICE

SCO 58-59, BANK SQUARE,

SECTOR 17B, CHANDIGARH

T. No: 0172-2704787  Fax: 0172-2704047

www.centralbankofindia.co.in

Prequalification & Selection of Architect / consultants

- Introduction

Central Bank of India was established as the first fully Swadeshi Bank by Sir Sorabhji Pochkhanawala in 1911 and was nationalized in the year 1969 by an act of Parliament of India. The Bank is a leading Public Sector Undertaking listed in BSE / NSE. More information is available on our website www.centralbankofindia.co.in. Bank apart from its Central Office at Mumbai is having various Zonal Offices,  Regional Offices and network Branches, ATMs  at various centers throughout the length and breadth of the country.

- Objective

The Bank is in the process of Construction of Administrative Office & Staff Residential Apartments on a plot admeasuring approximately One Acre at Sector 80, S.A.S. Nagar (Mohali). The Bank intends select architect/architectural firm who can undertake Consultancy Work for the design and supervision work of construction of building/s along with all required works land development, air-conditioning, electrification, data cabling, furnishing etc. The tentative preliminary project cost will be approx. Rs.20.60 Crores, subject to detailed project report and estimation by approved Project Architect.

- General Guidelines

  - Architect/architectural firms / consultant shall apply in detailed prescribed format, which can be downloaded from our web site

https://www.centralbankofindia.co.in/en/active-tender

  - Architect/ architectural firm / consultant shall also authorize the Bank to approach his Employers, Clients, Corporations, Organization, etc. to verify architect / consultant’s general reputation / competence. Confidential reports, if required may be called by Bank from any or all organizations which are referred in the application by Architect.

  - Application form shall be submitted in sealed envelope super scribing ‘Application for Selection of Project Architect / architectural firm for Construction of Central Bank of India Official & Staff Residential Complex at S.A.S. Nagar (Mohali), Punjab.

  - The application shall be submitted strictly in the format as mentioned along with the 	supporting documents.

  - The application shall be signed by the person/s on behalf of the Organization having necessary Authority/ Power of Attorney to do so. Each page of the application shall be signed and copy of Power of Attorney / Memorandum of association (Wherever applicable) shall be furnished along with application.

  - If the space in Performa is insufficient for furnishing full details, such information may be supplemented on separate sheet stating therein the part of Performa and serial number. Separate sheets may be used for each part of application. While filling up the application with regard to list of important projects completed or in hand the applicant shall only include major works handled by the firm.

  - The ability and competence of the applicant to render required services within the specified time frame will be a major factor while deciding the prequalification of architect/ architectural firm.

  - The applicant should ensure that the application is delivered/sent at the given address within/by/before the prescribed date and time as mentioned in the advertisement. If the application is delivered by Post or Courier, Bank shall not be responsible for delay or loss of the application.

  - Application containing false and / or incomplete information is liable for rejection.

  - The applicant should enclose draft (non refundable) of Rs.2,000/- (Rupees Two  Thousand Only) in favor of ‘Central Bank of India’, payable at Chandigarh. Exemption of tender fees shall be as per Government rules.

  - The Bank reserves right to accept or reject any or all the application.

  - Point of contact for any query should be AGM BSD / Architect/ BSD Incharge 0172 2702994-98 agmchanzo@centralbank.co.in, archchanzo@centralbank.co.in, gadchanzo@centralbank.co.in

  - If bidders/tenderers are not satisfied with Bank’s response then they may escalate their grievances to our Bank’s Independent External Monitors (IEM)

Sh. T.N.Tiwari     Email:  trivikramnt@yahoo.co.in

Sh. J.N.Singh          Email : jagadipsingh@yahoo.com

However, first point of contact shall be Bank and IEMs should be contacted later only if tenderer has some issue in tendering process and not satisfied with Bank’s response.

Note: IEMs should not be contacted for minor issues.

  - Completed document shall be submitted up to 17/07/2024 during /up to 3:00 pm to the office address as mentioned below:

Asstt. General Manager -BSD,

Central Bank of India, Zonal Office,

SCO 58-59, Bank Square, Sector 17B, Chandigarh.

Technical Bids shall be opened at 3.30pm same day in Bank’s Committee and no information/invitation will be sent separately /or as decided for a later date which shall be informed in writing to the bidders.

- The eligibility criteria for pre-qualification shall be as under :-

  - The applicant (Architect) should have minimum 07 years’ experience in the field of Comprehensive Architectural Services.

  - The architects/ architectural firms / consultants should have executed during immediate last 07(Seven) years as on March 31, 2024 at least

Three (03) similar projects of minimum value of Rs. 8.20 Crores, OR

Two (02) similar projects minimum value Rs. 10.30 Crores OR

One (01) project of Rs. 16.50 Crores

For any Government/Semi-Government/Fin. Institution/ Reputed Private Sector Organization. The applicant shall submit completion letter/relevant certificates from the Principal employer/Head of Deptt./Client on their official letterhead mentioning brief of project as a proof of his claim. Works done as sub-letting under/of other Architects will not be considered.

  - The architect should be a member of Council of Architecture (India). If the firm is a partnership firm or limited company then it should be as per Council of Architecture Public Notice dated 20.05.2013. At least one partner should be a member of Council of Architecture (India).

  - The architects/ architectural firms / consultants should have valid PAN & GST nos.

  - The architect/architectural firm should have an Office at Chandigarh (Tricity area i.e. Chandigarh, Panchkula and SAS Nagar Mohali).

  - Report regarding satisfactory performance from minimum 02 clients shall be submitted with application.

  - Consultancy Firm should have an average annual turnover of Rs.20.00 Lakh in last three years. (The details of professional fee received during said time period towards consultancy may be submitted/ indicated separately). Please attach 03 years ITR and Chartered Accountant’s certificate in this regard.

  - Earnest Money Deposit (EMD)-: A fixed sum of refundable Rs. 2.0Lakh (Rupees Two lakh only). For Micro and Small Enterprise entities registered under MSME, Exemption of EMD shall be as per Government rules. Relevant certificate in this regard should be submitted. EMD to be submitted in the form of Bank Draft or Unconditional Bank Guarantee, from a scheduled Bank, valid for 30 days after expiry of tender validity. EMD of unsuccessful bidders shall be returned after decision of qualifying bidders as per technical bid & EMD of unsuccessful bidders shall be returned after opening of financial bid.

  - The firm should have adequate organizational structure compromising of qualified architects, engineers, specialist, other technical officers and staff along with associated if any, to execute work of such nature and magnitude.

  - The firm should preferably have reasonable presence for any professional work in the area of the project or nearby districts, now or in the recent past.

Shortlisting will be strictly based upon professional expertise, proven capability and credentials.

Only shortlisted Architects as per technical criteria will be considered for next round of financial proposal/bid opening. Bank‘s decision shall be final in this regard.

Similar Work definition: Comprehensive Work of design and supervision of Institutional / Official Complex, Staff Housing/ Multi-storied Housing buildings over a minimum area of approx. 01.0(one) Acre for Government/Semi-Government / Reputed Private Sector organization/large Financial Institutions along with all required services viz obtaining various statutory approvals for successful execution of overall project, site development, water supply, sewage, electrical, fire detection & fighting, wired/wireless internet & security services etc.

- Conflict of interest –

  - The applicant/s should not have controlling shares / should not be owner of 2 firms submitting the applications

  - The applicant (including their staff and sub-contractors) should not have a business or family relations with such members of Bank staff who are directly or indirectly involved in the project.

  - The applications having conflict of interest shall be rejected.

6.0 	Process of selection of architect/architectural firms-Least Cost Selection (LCS).

Inviting applications and shortlisting of architectural firms as per their technical bid who meet the eligibility requirements listed in above Paragraph.

The shortlisting will be strictly based upon fulfilling the eligibility criteria. The decision of the Bank in this regard shall be final.

Under Least Cost Selection (LCS) a minimum qualifying mark (70 out of 100) for quality is established and indicated in the RFP, short-listed consultants have to submit their proposals in two envelopes. The technical proposals are opened first and evaluated. Proposals scoring less than minimum qualifying mark are rejected, and the financial envelopes of the rest are opened in public. The consultant with the lowest evaluated price (L-1) shall be invited for negotiations. There is no weightage for Technical score in the final evaluation.

In case the negotiation with the L-1 consultant fails, the consultant with the second lowest price shall be invited for negotiation, and so on.

Technical envelope should have all the required documents, EMD, tender fees DDs. Financial proposal should have only architectural fees offer. Both envelopes should be put in a big envelope super scribing “Application for Selection of Project Architect / architectural firm for Construction of Central Bank of India Official & Staff Residential Complex at S.A.S. Nagar (Mohali)”.

  - The offer letter shall be submitted in separate sealed cover. Fee quoted in the offer should be valid for at least 180 days from the last date of receiving the offer. Application with wrong /false documents will be liable for rejection at any stage.

Technical proposal -:

  - Due weightage shall also be given to the experience of the consultant in designing Bank/FI buildings including official buildings, staff quarters, training college buildings, quality of works executed, number of years in the architectural field, number of staff and their expertise, associates. The tentative marks allocated for different trades are as under (though it is just to give an idea for scrutiny only) :

| Sr. no. | Criteria Description | Rules for awarding marks | Max. marks |
| --- | --- | --- | --- |
| 1. | Financial strength of the firm |  | 20 |
| 1.1 | Average annual turnover for last three financial years | Min Rs. 20 lacs. |  |
| 2. | Man power |  | 20 |
| 2.1 | Number of skilled staff with technical qualification and experience - Architects / Interior Designers - Civil Engineers /Elect/HVAC Engineers/ Work Supervisors | 15 marks for 10 technical staff on rolls and 1 mark for every additional 1 staffs thereafter |  |
| 3. | Experience in proposed work |  | 15 |
| 3.1 | Number of years of experience in architectural work. (Minimum 5 years) | 10 marks for 5 years and 1 marks for additional every year of experience. |  |
| 3.2 | Number of similar work executed | marks for similar project 10 no. of Rs. 8.20 Crores or 15 no. of Rs. 10.30 Crores or 30 no. of Rs. 16.50 Crores | 30 |
| 3.3 | Similar work executed in the Region |  | 5 |
| 4 | Quality of service, strength of architect, Confidential reports etc. |  | 5 |
| 4.1 | Report regarding satisfactory performance from minimum 2 clients | 5 marks if yes | 5 |
| 5 | Total |  | 100 |

*Relevant certificates have to be enclosed in the technical proposal envelope.

GENERAL CONDITIONS

7.1	The right to suspend the process or part of the process, to accept or reject any or all applications at any stage of the process and/or to modify the process or any part thereof at any time without assigning any reason is reserved by Central Bank of India without any obligation or liability whatsoever.

7.2	The selected architect shall execute agreement with the Bank as per Bank’s format.

7.3	The architect/consultant shall preferably visit the plot to get acquainted with location and surrounding area. Chief Manager (BSD) or Senior Manager /delegated Officials at Zonal Office, Chandigarh may be contacted in this regard.

7.4	The project architect shall make applications to statutory / government / semi government bodies / organizations and obtain the necessary permission from them. The cost of liaison with the bodies shall be borne by Project Architect. However, statutory government charges shall be paid by the Bank (except the penalties which arise due to default, if any by Project Architect). The commencement certificate / approval from local municipal authorities must be obtained within 06 to 09 months time from the date of appointment letter or approval of the design whichever is later, unless and otherwise reasons for non-issuance of such certificates are beyond control.

7.5	The entire document shall be duly signed on all pages and returned to the Bank. The offer letter shall be submitted in separate sealed cover.

7.6	The Bank reserves itself the right to accept or reject any or all the offers.

- THE DUTIES OF PROJECT ARCHITECT

The applicant will sign an agreement with Bank, mentioning in detailed scope of the work and duties. Read Similar Works Definition, however the gist of the major role of the applicant is given in brief as under:

  - Take Bank’s instruction, prepare make approximate estimate cost by cubic measurements or otherwise,

  - Prepare drawings sufficient for making applications for work licenses/approvals etc to local authorities or for other approvals, prepare working drawings, prepare structural drawings from structural consultant if and as required,

  - Prepare specifications, prepare bills of quantities, and detailed estimate with rate analysis,

  - Prepare tender documents and issue sufficient number of copies as may be required for calling the tenders.

  - Advise on preparation of a panel of contractors to be invited for tendering,

  - Assist in obtaining tenders, advise on tenders received, prepare contract documents,

  - Nominate, hire and instruct Service Consultants (if any), coordinate activities of all Consultants,

  - Prepare such further details and particulars as are necessary for the proper carrying out of the works,

  - Advise Bank on technical and financial implication of the deviation/ amendments (if any), from the approved scheme,

  - Carry out regular supervision, arranging site meeting on regular interval, measurement, quality control, variation management and ensuring smooth completion of works. For day-to day Bank will deploy technical staff with the help of applicant.

  - To issue sufficient copies of drawings / instructions to the Bank and contractors as may be necessary to carry out the project.

  - Obtaining various approvals from local/statutory authorities as required during the execution/completion of the project.

- THE SCHEDULE OF PAYMENT OF FEE

  - On the approval of sketch design and preliminary estimates – 10%

  - On preparation of required drawings and particulars for structural work, services, etc. for applications to be made to Bank and Local Authorities for approval and obtaining the same from the local authorities                                        – 15%

  - On approval of detailed architectural working drawings and structural/ service drawings sufficient for preparing detailed estimates of cost – 25%

  - On approval of detailed estimates, preparation of tender documents, tender process and advising on tenders received                                          – 35%

  - On award of job to the successful tenderer                           – 50%

  - For making periodic visits for inspection and quality surveillance preparing other details and drawings as may be required during execution along with variation control to be paid progressively with execution of the work           – 90%

  - Issue of completion certificate and as - built drawings        – 95%

  - At the end of Defect Liability period of contracts            – 100%

  - The fees as stated hereinabove will also be applicable to engineering services work that may be assigned to the Project Architect.

  - The fees as stated herein above will be adjusted on the basis of latest available estimated cost or if tenders have been received then on the lowest bonafide tendered cost. For stage 9.6 onwards progressive payment will be made on the basis of cost of works done.

  - Fees for Bought out items shall be calculated at rate of 25% agreed fee.

10.0	Design Brief & Description of Project: The project involves the construction of tentatively 2 Blocks - Administrative Office & Multi-storeyed Staff Residential Apartments on approximately one acre land (approx. half acre each) at Sector 80, S.A.S. Nagar (Mohali). The project shall be developed on modern architectural theme to showcase it as a Corporate Centre, reflecting the image of Bank as a pioneer in innovative and unique Banking activities of the Industry.

Requirements *Administrative Office comprising of following:

1). Bank’ Offices as per requirements

2). CBOTC (Training College) with Hostel

3). Various Offices

4). Bank’s Branch & Canteen / Cafeteria	       - (Around 40 Persons)

& Allied services

- Requirements *Multi-storied Residential Apartments for Bank Staff:

  - Scale – VI,VII Senior Executives	-max Units (3BHK) as per norms

  - Balance 2BHK flats                          -max Units (2BHK) as per norms

  - Community Facilities as per GMADA/local authority Norms.

- *Basement – Parking & Building Utilities/Services

(*DETAILED PROJECT REQUIREMENTS WILL BE GIVEN TO THE ARCHITECT SELECTED.)

SCOPE OF WORK DETAILS : 	Central Bank of India, Zonal Office, Chandigarh intends to avail comprehensive architectural services viz preparation of Survey Plan of the Site/testing of the bearing Capacity, Contour plan showing the NSL of Site /layout Plan/ Architectural Drawings as per requirement of the GMADA, SAS Nagar Mohali in accordance with guidelines and space standards for barrier free built Environment for Disabled and Elderly persons and guidelines for setting up of Public Areas, Technical areas e.g. Auditorium/Foyer including internal Electrical Services/ Internal Public Health Services (Plumbing), Toilet details, stair case details, joinery details, drawings for shutters etc. / layout plan including Designing & Planning of Net work of roads, sewerage system (including disposal work), drainage, water supply system, External Electrification & Street Lighting Landscaping, Horticulture, signage, designing of entry & welcome gates, interior design/decoration, structural designs including foundation design duly vetted from any Government Engineering College or NITs, Preparation of detailed estimates on the basis of CSR (Punjab)/DSR(Delhi) plus latest sanctioned ceiling premium, preparation of model of the project and preparation of works / communication system/ power supply system /Fire Fighting/ flooring/false ceiling/ internal lighting / Cladding / Rain water Harvesting system or any other activity /services required for completion of work to the entire satisfaction of Bank/Officer-in-Charge. Various Consultants required for the project e.g. Structural/ Electrical/ HVAC/ Landscaping etc shall be hired by the appointed Project Architect so they should consider this aspect also before quoting fees. Bank encourages a healthy competition and too low quoted fees may be viewed unfavorably. The Consulting Firm shall be responsible for following scope of work:-

- Preliminary Planning Stage: Preparation of the concept drawings & detail drawings to be evolved as per provisions / rules applicable to the area of all buildings, guidelines and space standards for barrier free built Environment for Disabled and Elderly persons and guidelines for setting up of Public Areas, Technical areas, Auditorium and Foyer, services both internal and external including electrical, communication, fire fighting, anti-termite, earth quake resistant, landscaping etc. indicating complete scope of work, specification and cost estimates for each sub head / package. Obtain approval of all local and other authorities.

- Drawings for Estimates: Prepare drawings, including structural designing of all works mentioned above in consultation with the Officer-in-Charge and also obtain approval from wherever required for all subsequent changes / deviations and to make available all documents pertaining to the same to the Officer-in-charge. The structural drawings should be got proof checked and approved from any Government /Autonomous Engineering Institute / Research Institute.

- Detailed Estimate and Tendering: Prepare and supply DNIT along with detailed of calculations for all items of work together with detailed specification and detailed architectural drawings, foundation drawings. Detailed estimate on standard schedules justified cost based on DSR/CSR (Punjab) applicable in Punjab State or norms approved by Punjab PWD B&R Branch and tender documents sufficient to enable the Officer-in-charge to invite tenders for each sub-head/ packages.

- Directing and coordinating all Architectural, structural Engineering and surveying work and prepare (with help of Officers, surveyor and other Consulting Firms, as necessary) complete working details, schedules, specifications and bill of quantities to describe the whole project adequately for the purposes of taking approval from the authorities and for placing the main and other subsidiary contracts

- Working Drawing Stage: Preparation of detailed drawings of Architectural, Structural, Electrical, Landscaping Services etc. and all the services mentioned under the Head INTENT including drawings showing details of all utility services internal & external details of specification of all special items of work that may be involved and preparation of model of the project.

- Construction Stage: Supply all Architectural, Structural and Services working drawings, specification and details which may be required for proper execution of the work. Prepare and obtaining approval from the Officer-in-charge for any material deviation in design of cost of the working drawings schedule and specifications for the approval scheme of approved cost of the work.

- On Completion: Prepare completion drawings including elevations and section and structural details indicating details of building and all services of built and supply four (4) sets of completion drawings to Officer-in-charge including one soft copy & help Bank is getting Completion/Occupancy certificate. These are in addition to drawings details mentioned in above clauses. Obtain approval of all local and other authorities.  for completion certificate of project as per the requirements and also prepare required drawings for the same.

NUMBER OF DRAWING SETS AND DOCUMENTS TO BE SUPPLIED

Consulting Firm shall submit to the Officer-in-charge the following:

| 1 | Supplying of Design/ Drawings for Architectural/ Civil/ structural design / electrical / plumbing / interior design/ landscaping / lighting / Network of Roads, sewerage, drainage, water supply/ graphic signage/ communication system/elevator /power supply system/ fire fighting/ data cables/ flooring/false ceiling/ internal lighting/paneling/ furniture/ cladding/ storage units/acoustics / anti-termite/ earth quake resistant and rain water harvesting system etc | Four (4) sets for each services for the project |
| --- | --- | --- |
| 2 | Supply of detailed estimate of each service as mentioned at 1 above. | Three (3) sets of each work of the project |
| 3 | Supply of DNIT/ Tender Documents of each service as mentioned at 1 above. | Three (3) sets of each work of the projects |
| 4 | Completion drawings of all services | Four (4) sets |
| 5 | Back up of all the documents mention from (1) to (3) above | CD - 2 nos |

ACTIVITY TIME FRAME

|  | Activity | Time Frame | Remarks |
| --- | --- | --- | --- |
| 1 | Pre construction activities |  |  |
| a | Preliminary design | 30 days |  |
| b | Final design | 60 days | Final design to be Submitted after approval of Preliminary design by the Officer-in-charge. |
| c | Preparation of drawings for detailed estimate | 30 days |  |
| d | Tender document with “DNIT” and detailed estimate and draft tender document for calling of tenders. | 45 days |  |
| 2 | During construction |  |  |
| a | Preparation of working drawings as and when required | 01 week advance |  |
| b | Supply of working drawing good for each activity for construction during progress of work | 01 week advance |  |

GENERAL CONDITIONS

      - The design shall be economical & Use of modern concept and innovative design shall be given weightage.

- Each page of the documents should be signed by the bidder or his authorized representative. Offer shall be submitted in sealed cover super-scribing the name of the work on the cover.

- The project should be designed confirming to the prevailing Building bye-laws, NBC, guidelines and space standards for barrier free built environment for disabled and elderly persons, guidelines for setting up Public Areas, technical areas, auditorium & foyer as applicable. The Architect/Consultant will have to make modifications in the Architectural Drawings and Structural Drawings as per the requirement of the Bank’s Higher Authorities or as required by Local Civic Authorities at any stage during the currency of the work for which no extra payment will be made.

- Central Bank, Zonal Office, Chandigarh shall recover the security deposit from the work done of the Consulting Firms @ 10% from each running account bill subject to a maximum of Rs.2.00 lacs. The security shall be released within one month from the date of successful completion of project to the entire satisfaction of the Bank/Bank’s Officer-in-Charge.

- The interim payment of consultancy bill in respect of complete items of work shall be made on Pro-rata basis fees being worked out based on quantum of work completed for different item of work.

- Consulting Firm shall submit the time frame for completion of various stage of the job of works assigned to them.

- Consulting Firm shall also submit all originals in form of soft copy (CD/Pen Drive etc) of tracing of the drawings and other documents like estimates, analysis of rates of various items & tender documents.

- Statutory taxes or any kind of tax and its increase or decrease after submission/ opening of offers shall be adjusted as per applicable Government Rules.

- Termination: In case Architect/Consulting Firm fails to fulfill its duties diligently as per the completion time schedule, its services shall be terminated with 15 days notice and security amount will be forfeited.

- In the event of any dispute between the parties hereto arising out of or in any way relating to or concerning this consultancy work the same shall be referred to the Sole Arbitrator not below the rank of Chief Manager either serving or retired appointed by the Zonal Head/Field General Manager, Zonal Office, Chandigarh. The award of the Arbitrator so appointed shall be final and binding on both the parties. The Arbitrator shall give written reasons for his award.

- Consulting Firm, whose tender is accepted will be required to furnish an Indemnity Bond as per format approved by the Officer-in-charge on non-judicial stamp paper of requisite amount that in case of failure of structure due to inadequacy/deficiency in structural design/drawings within ten years from the date of completion of buildings, the charges of rehabilitation of the buildings and any loss on that account will be borne by the Consulting Firm.

- All design and drawings should be based on original concept (Should not be copy of the any of the project situated anywhere) and copy right of all drawings and design made by the Consulting Firm will remain the property of the Central Bank.

- A continuous liaison shall be maintained by the Consulting Firm with the Officer-in-charge/Bank’s Architect/Engineer during preparation and presentation of Design and Drawings. Any advice tendered by the Officer-in-Charge in respect of the Design and Drawings shall be binding on the Consulting Firm.

- The Consultant will have to prepare presentation drawings, perspective view, model and power point presentation of the project, the copies of which will be retained by Central Bank of India. The Consultant shall also supply presentation drawings, perspective views, accommodation & area details for the brochure and the advertisement of the scheme.

- Consulting Firm will be responsible for the correctness of Design and Drawings of all the components of the building.

- Consulting Firm has to make his own arrangements for laboratory, machinery, equipments and any other items required directly or indirectly for preparation and presentation of Design and Drawings.

- No claim shall be entertained on account of increase in the wages of the staff, material etc. required directly or indirectly for preparation and presentation of Design and Drawings.

- Officer-in-charge reserves the option and right to cancel the Contract if it is found during the currency of the Contract that the speed of the work done does not commensurate with the time elapsed and re-allot the same to any other Consulting Firm with due notice without liability of any kind of payment or any compensation.

- Rates quoted by the Consulting Firm shall be for complete work in all respects and include supply/carriage of laboratory equipments, machinery, material royalty, octroi charges and no claim on account of fluctuation of price due to any cause shall be entertained.

- Taxes including GST, if any, shall be paid by the Consulting Firm themselves directly to the respective departments in accordance with the rules and regulations in force from time to time without intervention of Central Bank of India, Zonal Office, Chandigarh. However Income Tax shall be deducted at source from the payments due to the Consulting Firm as per provisions of Income Tax Act.

- Nothing extra shall be paid for material/labor required for the work directly or indirectly and the rates to be quoted by the Consulting Firm shall include all the charges thereof.

- Consulting Firm shall strictly follow the methodology and sequences of operation etc. as given by it in its technical data and accepted by the officer-in-Charge. Any modification can be allowed only with the prior approval of the officer-in-Charge.

- Central Bank shall be entitled to copy right of all the documents, drawings and other materials produced for the purpose of this project by the Consulting Firm who shall not use any of such documents or material for any other purpose other than project except with the permission of the Officer-In-Charge. The Corporation shall have the full right to utilize fully or partly any part of the Design/Drawings on any other building of Central Bank.

- Any other detail which is considered necessary and relevant to the work and not covered in the scope of work above and directed by Officer-in-Charge shall also be deemed to have been covered in the scope of work and shall be carried out by the Consulting Firm without any extra cost to Central Bank.

- All disputes regarding this work shall be restricted to Civil Courts located at Chandigarh.

- Officer-in-charge or his representative shall have the right to watch and supervise the work.

- Consulting Firm should be available at site of project for discussion or assistance, if required by the Officer-in-charge without any extra charges.

- Officer-in-charge reserves the option to take away any item of work or any part thereof at any time during the currency of the Contract and re-allot it to any other Consulting Firm with due notice to the Consulting Firm without liability of any kind or payment of any compensation.

- Structural design should cater for the telephone lines, public health services, electric lines, electric conduits etc. The structural design should also cater for firefighting/air conditioning if required.

- Consulting Firm shall submit the Price Bid to cover all the professional charges for the service rendered for the jobs mentioned above on lump sum basis.

- Time schedule and payment schedule for supplying the Design, Drawings and various documents are explained under the head “STAGE OF PAYMENT OF FEES” & “ACTIVITY TIME FRAME”.

- In case, the Consulting Firm abandons the work for any reason whatsoever or becomes incapacitated from providing Services as per aforesaid agreement then Central Bank will make the payment of the Consultancy Charges payable for the services so provided up to that stage stipulated in the agreement after making 10% (Ten Percent) deduction of the Total Fees payable to the Consulting Firm under this agreement. In case, the 10% deduction of Total Fee payable to Consulting Firm is more than the amount payable to the Consulting Firm then the Firm has to deposit the balance amount.

- In case the Central Bank decides to scrap the project due to any reason at any stage, the fee as payable as per agreement up to that stage will be paid to the Consulting Firm.

- In case the Central Bank decides to change the scope of the work during the currency of the scope of the work and the Central Bank decide to avail Consultancy Services according to the changed scope of work from the Consulting Firm then the Consulting Firm will have to provide the services as per the new concept at the Fee already decided. However, the payment up to the stage the services provided by the Consulting Firm as per the previous concept will also be paid. The payment of different stages will be determined as per the stages prescribed in the agreement.

- Consulting Firm shall agree to redesign at their cost any portion of their Engineering and design work which due to their failure to use a reasonable degree of design skill is found defective within ten years from the date of start of regular use of the portion of the work affected. Central Bank shall grant right of access to the Consulting Firm for inspection of those portions of the work as are claimed to be defective. Central Bank may make good its loss by recovery from the Consulting Firm in case of failure to comply with the above clause.

- Consulting Firm shall be bound to repeat the above said work, if scope of work in increased due to change of the policy/building related Bye-laws by the Government in the same cost. No claim shall be entertained on this account.

- Consulting firm shall consider all necessary provisions of the I.S Codes in respect of the Structural Loads & Earthquakes.

Asstt General Manager BSD,

Central Bank of India, Zonal Office,

Chandigarh

To,

Asstt. General Manager

Business Support Department,

Central Bank of India,

Zonal Office, Sector -17B,

Chandigarh

Ref: 	Application for selection as Project Architect

Dear Sir,

I / we have read and understood the instructions and the Terms & Conditions mentioned in the application form. I / we do hereby declare that the information furnished in the application and the supplementary sheets are correct to the best of my knowledge and belief.

I / we authorize Bank to approach our employers, clients, corporation organization etc. to verify the facts submitted by us.

Signature of applicant/authorized signatory with office seal

Name:

Designation:

Address:

Place

Date:

To,

Asstt. General Manager

Business Support Department,

Central Bank of India,

Zonal Office, Sector -17B,

Chandigarh

Ref: 	Architectural Fees offer for Construction of Bank’s Official and Residential Complex at SAS Nagar Mohali

Dear Sir,

I / we have read and understood the instructions and the Terms & Conditions mentioned in the application form. I / we do hereby declare that the information furnished in the application and the supplementary sheets are correct to the best of my knowledge and belief.

I / we quote my/our offer of Architectural consultancy fees @.................% (…………………………………………..in words) for the referred Project.

Signature of applicant/authorized signatory with office seal on Official letterhead.

Name:

Designation:

Address:

Place

Date:

(Note: Offer to be submitted in a separate sealed envelope marked as financial bid. Only those financial bids will be opened which qualify the technical criteria. )

Information to be furnished by the applicants

| 1 | Name of the organisation |  |  |
| --- | --- | --- | --- |
| 2 | Address | Postal address |  |
|  |  | Telephone nos |  |
|  |  | E-mail address |  |
| 3 | Year of establishment |  |  |
| 4 | Status of the firm (Enclose copy) |  |  |
| 5 | Name of Directors/ Partners? Proprietor |  | i) ii) iii) |
| 6 | Whether registered as a member of the Indian Institute of Architects / Council of Architecture. If so, mention number and date. (Enclose copy). Note: Refer Criteria; Membership of Council of Architecture is a must. |  |  |
| 7 | Name and address of Bankers |  | i) ii) iv) |
| 8 | Name of projects to be considered for fulfilling eligibility criteria executed during last three years by the firm. (Details to be furnished in proforma 1) |  | i) ii) |
|  | Important major projects on which the firm is engaged at present and their estimated cost, stage of work viz. planning and construction, the full address of clients shall be indicated against each project. (Details to be furnished in proforma 3) |  | i) ii) iii) |
|  | If you are registered in panel of other organisation / Statutory bodies such CPWD, PWD, MES, Banks, etc., furnish their name, Category and date of registration. |  | i) ii) iii) iv) |

List of Documents to be enclosed with application form.

      - Status of the Firm / Registration certificate/ Memorandum of association

      - GST registration certificate

      - Income tax certificates

      - Proforma – 1

      - Proforma – 2

      - Proforma – 3

      - Proforma – 4

      - Color Photographs of major work executed ( or E-links/Web-links/Pen drive are also accepted)

      - Completion certificates & work orders from clients for the work fulfilling eligibility criteria.

      - Turn over certificate from Chartered Accountant.

      - Demand draft / pay order of non-refundable Rs.2,000.00 (Rupees Two Thousand only) in favor of ‘Central Bank of India’ payable at Chandigarh. Exemption of fees, if any, shall be as per Government rules.

      - EMD of refundable Rs. 2.0 lakh in favor of ‘Central Bank of India’ payable at Chandigarh. Exemption of EMD shall be as per Government rules upon submission of relevant certificates.

      - Authority letter to sign the application wherever required (wherever applicable)

      - Other documents/any other documents as specified in support of application

      - Integrity Pact

      - Please put initials with seal on each page, including on Integrity Pact

DETAILS OF REGISTRATION

| Sr. no | Name of organization / department | Registration no. | Date / year of registration | Enclosed proof |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Yes | No |
| 1. | Registrar of firms and societies/ Registrar of Companies, if and wherever applicable |  |  |  |  |
| 2. | Income tax department (mention PAN no. with copy of latest income tax clearance certificate) |  |  |  |  |
| 3. | GST (Enclose copy of latest clearance certificate / proof of depositing the tax) |  |  |  |  |
| 4. | Council of Architecture registration |  |  |  |  |
| 5. | Details of EPF account and registration, if available |  |  |  |  |

FINANCIAL STATUS

| Sr. no | Financial year | Turnover/ Fee Income of the firm (in Rs. Lacs) | Profit / loss | Enclosed certified copies of audited balance sheets / chartered accountant’s certificate. |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Yes | No |
| 1 | 2020 – 2021 |  |  |  |  |
| 2 | 2021 – 2022 |  |  |  |  |
| 3 | 2022 – 2023 |  |  |  |  |

* Inform about proposed filing of 2023-24 also if done.

PROFORMA –1

PARTICULARS IN RESPECT OF WORK EXECUTED

| Sr. No | Name of the work/ project executed with address | Short description of work executed | Name and address of owner / consultant | Value of work executed | Stipulated time of completion | Date of commencement | Date of completion | Any other relevant information |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |

Signature of the Applicant

____________________________________________________________________________________________________________________________

PROFORMA- 2

LIST OF KEY PERSONAL PERMANANTLY EMPLOYED

| Sr.No. | Name | Designation | Qualification | Experience | Years with the Firm | Any other information |
| --- | --- | --- | --- | --- | --- | --- |

Signature of the Applicant

PROFORMA –3

PARTICULARS IN RESPECT OF WORK IN HAND

| Sr. No | Name of the work/ project executed with address | Short description of work executed | Name and address of owner | Value of work executed | Stipulated time of completion | Status Of Work | Any other relevant information |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |

Signature of the Applicant

____________________________________________________________________________________________________________________________

PROFORMA – 4A

ASSOCIATES

S. NO.		Name				              Address				          Phone No		                  e-mail

1.

2.

3.

4.

5.

Note: The firm shall submit consent letter from the concerned firm along with the application

PROFORMA – 4B

Reference

S. NO.		Name				              Address				          Phone No		                  e-mail

1.

2.

3.